## Sheet1
Code architecture modules
Idx | Module | Owner | ETA | Status
0 | Data extraction
| Extracting news articles from urls | Kannan |  | Completed
TARGET Compeletion Date [0-3]
1 | Exploratory data analysis |  |  |  | 24/06/2020
| Basic Exploratory statistics | Kannan |  | Completed
| Extend Exploratory statistics for additional attributes we are generating | Kannan/sandeep |  | Completed | 4 days for Project report & PPT
| Record/write detailed observations | Kannan
2 | Feature Engineering
| Feature importance scoring by attributes | Kannan |  | Completed
| Generated featuers (w2v, subjec/polarity, numeric features) - feature significance scoring & Feature stitching | Kannan |  | Completed
| Creating additinoal Numerical Features (ref UCI) + Feature importance scoring | Sandeep/Venkat
| keywords popularity / average shares with keyword / min/max keyword share (similar to UCI) | Venkat
| Recreatiion of RAW (17) features, for end to end (real time) demo. High/least imporatant features (recreate/impute) | Venkat
| Text Features - keywords to vector, vector --> PCA, PCA --> Attribute importance | Venkat |  | Completed | top priority
| Text Features - NER to vector, vector --> PCA, PCA --> Attribute importance | Venkat |  | Completed | we need see the pipeline e2e for available features. Rmse our current stand
| Text Features - NER count by types--> Attribute importance | Venkat |  | Completed
| Preprocessing of text data (e.g lowercase conversion, removing punc, etc) before generating vectors/pca | Venkat
| Text Features - article content to sentiment & subjectivity + Feature importance scoring | Kannan |  | Completed
| Normalizing the features | Sandeep |  | Completed
| LDA/NMF/LSI topics and doc to LDA_topics distance | Kannan |  | Completed
| Run feature stitching/seleaction with LDA/NMF/LSI featues | Kannan | 2020-06-20 | Completed
17 raw features
3 | ML Model |  |  |  |  | > 6 feature importance
| Traditional ML Benchmarking | Kannan |  | Completed |  | 11 imputation | least importance feature
| Traditional ML Tuning and Inmprovement | Kannan
| hyper parameter tuning - ElasticNet | Kannan | HIGH PRIORITY | Completed
| hyper parameter tuning - svm/ Lasso | Kannan
| Writeup about traditional algorithms / comparison / justification why we chose algorithm-X https://towardsdatascience.com/whats-the-difference-between-linear-regression-lasso-ridge-and-elasticnet-8f997c60cf29 | Kannan
| Deep Learning basic pipeline | Sandeep |  | Completed
| Deep Learning Tuning and Improvement | Sandeep |  | Completed
| ran traditional/DL regression with featureEngg data (with/without outliers) | Sandeep |  | Completed
4 | Project Report
| Write detailed project report |  | 5 days
PPT
| real time demo pipeline with single url (end to end pipeline) | Sandeep